## Gantt Chart
ID number | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE |  |  | PHASE TWO |  |  | PHASE THREE |  |  | PHASE FOUR |  |  | PHASE FIVE
[7 empty] | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 5 | WEEK 6 | WEEK 7 | WEEK 8 | WEEK 9 | WEEK 10 | WEEK 11 | WEEK 12 | WEEK 13
1 | Project Conception and Analysis | Sherwin, Theo, Ben, Kyle | 2023-01-02 | 2023-01-09 | 8 d | 100%
2 | Requirements gathering | Theo | 2023-01-02 | 2023-01-05 | 4 d | 100%
3 | Meet with Stakeholders | Sherwin, Theo, Ben, Kyle | 2023-01-06 | 2023-01-07 | 2 d | 100%
4 | System Documenting | Sherwin | 2023-01-08 | 2023-01-09 | 2 d | 100%
5 | Finalize Analysis |  | 2023-01-09 | 2023-01-09 | 1 d | 100%
6 | Project Design and Planning | Kyle, Sherwin, Theo | 2023-01-09 | 2023-01-27 | 18 d | 35%
7 | Design Database | Theo, Sherwin | 2023-01-09 | 2023-01-13 | 5 d | 100%
8 | Design Interface | Sherwin, Kyle | 2023-01-14 | 2023-01-16 | 3 d | 10%
9 | Create Design Architecture | Kyle | 2023-01-17 | 2023-01-20 | 4 d | 0%
10 | Create Design Specifications | Kyle, Theo | 2023-01-21 | 2023-01-26 | 6 d | 0%
11 | Finalize Design |  | 2023-01-27 | 2023-01-27 | 1 d | 0%
12 | Project Development | Ben, Theo | 2023-01-27 | 2023-02-21 | 25 d | 10%
13 | Develop System Modules | Theo | 2023-01-27 | 2023-02-09 | 14 d | 20%
14 | Develop System Databases | Ben, Theo | 2023-02-10 | 2023-02-15 | 6 d | 0%
15 | Integrate System Modules | Ben | 2023-02-16 | 2023-02-17 | 2 d | 0%
16 | Integrate System Databases | Ben | 2023-02-18 | 2023-02-19 | 2 d | 0%
17 | Perform Inital Tests | Theo | 2023-02-20 | 2023-02-21 | 1 d | 0%
18 | Development Finished |  | 2023-02-21 | 2023-02-21 | 1 d | 0%
19 | Project Testing / Monitoring | Sherwin, Theo, Ben | 2023-02-21 | 2023-03-09 | 16 d | 30%
20 | Perform System Test | Sherwin | 2023-02-21 | 2023-02-26 | 6 d | 55%
21 | White Box Testing | Theo | 2023-02-27 | 2023-03-04 | 6 d | 0%
22 | Document Errors and Issues found | Sherwin, Theo | 2023-03-05 | 2023-03-06 | 2 d | 0%
23 | Correct Errors | Ben | 2023-03-07 | 2023-03-08 | 2 d | 0%
24 | Finalize Testing |  | 2023-03-09 | 2023-03-09 | 1 d | 0%
19 | Project Implementation | Ben, Kyle | 2023-03-09 | 2023-03-23 | 15 d | 0%
26 | On-site Installation | Ben | 2023-03-09 | 2023-03-10 | 2 d | 0%
27 | Server Installation | Ben | 2023-03-11 | 2023-03-12 | 2 d | 0%
28 | Formulate Support Plan | Kyle | 2023-03-13 | 2023-03-23 | 11 d | 0%
29 | Completion | Kyle, Sherwin | 2023-03-24 | 2023-03-31 | 7 d | 0%
30 | System Maintenance | Sherwin | 2023-03-24 | 2023-03-31 | 7 d | 0%
31 | Evaluation | Kyle | 2023-03-24 | 2023-03-31 | 7 d | 0%